## Cover
The
Airline Sourcing Project
Stress Test
from
Smooth Skies or Rough Air Ahead?
This tool is designed to help travel and procurement managers better understand and manage the complexities involved in airline sourcing projects, and to test their projects for critical stress points before any preventable issues arise. Use this tool to generate a rigorous and insightful analysis of the nearly 100 elements that we believe are important to managing a successful sourcing project. Low scores are signs of likely stress and potential problems - clearly these are areas that you'll want to focus on before or during the sourcing project. While high scores won't gaurantee that you'll achieve record-breaking savings, they do mean that you'll very likely enjoy a well-managed, low-stress project that has most of the cards stacked in your favor for strong and successful airline sourcing and negotiations. For more information on managing airline sourcing projects, contact Scott Gillespie at Scott.Gillespie@Travel Analytics.com or by phone at +1 440 248 4111

## Let's Go
Ready? Let's Go! Here is a checklist to be sure you've properly completed the questionnaire: 1Read the "Directions" worksheet and review the "Scoring Sample" worksheet. 2. For a quick read on your individual airline sourcing situation, fill in the yellow-shaded cells on the "Quick Version" worksheet. It takes about 5 minutes to complete. 3. For a more detailed look at your individual airline sourcing situation, fill in your answers in the yellow-shaded cells on each of these ten worksheets: * "Goals" *"RFP Process" * "Resources" *"Analysis" * "Credibility" *"Negotiations" * "Support" *"Decisions" * "Control at Point of Sale" *"Contracting" (Be sure you start at the top of each worksheet and fill in each yellow-shaded cell) 4. Review your results as shown on the "Scores" worksheet. If you wish, you may enter different weightings on this page for each of the ten dimensions. 5. Once you've finalized your answers, you may wish to review the dimensions where your score is less than what you believe it needs to be. Keep in mind that the score for an element may depend on the point in time when you evaluate it. There are several solutions typically used to improve a project's overall score. These include: * Clarifying key issues such as project goals, definitions, roles and decision processes * Strengthening senior management's support on key issues of travel policy and enforcement, typically by building solid business cases * Obtaining more or better resources, such as data, budgets and staff * Revising a project plan's timetable * Learning more about the airline industry and the drivers of successful airline negotiations We hope you find this tool useful, and we wish you the best in your efforts!

## Directions
Airline Sourcing Project Stress Test
Provided by Travel Analytics
www.travelanalytics.com
Greetings! This workbook is designed to evaluate a company's airline sourcing project using Travel Analytics' Stages Of Excellence framework. While sourcing projects do vary across companies, we have found that there are many important issues common to most of these projects. This workbook represents our views and experience gained from working with dozens of project teams from companies of all sizes. We hope you will benefit from this tool! Guidelines for using this workbook: There are 95 different elements to be scored. They are organized into ten dimensions, each of which has its own worksheet. Most of these ten dimensions have been further broken down into separate categories whose scores are not explicitly calculated, but can be used for your reference. Users should enter two scores for each element: 1) "now" should reflect your assessment of the situation on your current project and 2) "most likely" should reflect where your organization can generally expect to be on most projects, now or in the near future. These scores, which should only be entered in the yellow-shaded cells, will be averaged, and the results posted on the "Scores" worksheet. Each element's "now" score has been set as a default to 1.0, and each element's "most likely" score has been set to a default of 2.0, so that you can view a chart showing all dimensions on the "Summary" worksheet. You should be sure to enter your own scores and goals in each of the yellow boxes. Before going through the detail of scoring all 95 elements, you may want to start with the "Quick Version" worksheet, which gives you an approximation for the more detailed exercise using only 15 questions. You'll need about 20 minutes to complete the entire questionnaire; you won't need any data - just your knowledge of your organization and the airline industry. Scores and Weightings We have selected criteria that describe a wide range of performance. Stage 1 is poor, while Stage 4 is excellent. Please note that the criteria for Stage 4 are set intentionally high. This means even the best sourcing projects will not likely score in Stage 4 across all, or even most dimensions. Stage 4 can best be viewed as a stretch goal; many well-managed projects will probably not score much above Stage 3. You may enter any value for a score or a goal, from 0.5 to 4.5. You may use partial numbers, such as 2.5 or 3.3, to make a more accurate assessment. The average of the element scores is used to calculate the dimension's score. The average of the ten dimension scores is used to calculate the total airline sourcing score, but if your situation requires different weightings for individual dimensions, you can feel free to enter the appropriate proportions on the "Scores" worksheet. Suggestions for improving this tool are definitely welcome! Please contact us with your thoughts. Thank you. Travel Analytics, Inc. www.travelanalytics.com +1 (440) 248-4111

## Scoring Sample
GOALS | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Clarity of Terms (on this project)
G1 | Definition of savings | Not defined, or very impractical | Fairly vague | Fairly clear | Very clear and practical | 2 | 3.2
G2 | Definition of quality | Not defined, or very impractical | Fairly vague | Fairly clear | Very clear and practical | 1 | 2
G3 | Definition of risk | Not defined, or very impractical | Fairly vague | Fairly clear | Very clear and practical | 1 | 2
|  |  |  | Avg. Score | GOALS
Enter your scores and your goals in these yellow boxes. Use any number between 0.5 and 4.5.
Each element relates to the category within which it is listed and, more generally, to the overall dimension on whose worksheet it is located. There are three elements in this sample. Each one relates , in this sample, to how clearly terms are defined on this particular project. Each element is a topic or issue. You then evaluate the four criteria in the row to the right of the element, and score your project accordingly
Dimension
Category
Now
Most Likely
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,
Questions? Give us a call at +1 (440) 248-4111. We'll be glad to help!
Criteria
Elements
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
The grey boxes show the calculated averages. These boxes have formulas in them; don't enter numbers into these boxes. These scores are posted to the "Summary" worksheet, and are used in the final calculations.
Airline Sourcing Project Stress Test - Scoring Sample Page

## Quick Version
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
QUICK VERSION | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Q1 | Goals for this project | Not yet set, or very unrealistic | Appear very hard to meet; probably not achievable | Appear fairly hard to meet; may not be achievable | Aggressive but achievable | 1 | 2
Q2 | Deadline for finishing this project | Definitely impossible | Only if we cut some important corners | Appears fairly achievable | Very achievable | 1 | 2
Q3 | Quality of airline spend data | Don't yet know, or very poor | Fairly poor | Fairly good | Very good | 1 | 2
Q4 | Quality of our people on this project | Can I skip this question? | Not yet sure | Mostly fair or good | Mostly very good or excellent | 1 | 2
Q5 | Project budget | What budget? | Very limited | Fairly limited | Adequate or good | 1 | 2
Q6 | Our credibility with our key airlines | Poor | Fair | Good | Great | 1 | 2
Q7 | Senior Management's willingness to enforce travel policies | None or very low | Fairly low | Fairly high | Very high | 1 | 2
Q8 | Our travelers' compliance with key travel policies | None or very low | Fairly low | Fairly high | Very high | 1 | 2
Q9 | Overall strength of our travel policy | What Travel Policy? | Fairly weak | Fairly strong | Very strong | 1 | 2
Q10 | Other tools and processes for controlling airline purchases | Very weak or non-existent | Fairly weak | Fairly strong | Very strong | 1 | 2
Q11 | Overall structure and quality of our RFP process | Very informal and unstructured | Fairly informal; quality is hard to evaluate | Fairly formal with good quality | Very structured and high quality RFP process | 1 | 2
Q12 | Overall process for analyzing airline pricing, quality and contract risk | Very subjective and unstructured | Fairly subjective; limited structure | Fairly objective and structured | Very objective and well structured | 1 | 2
Q13 | Negotiating power vs. our key airlines | Vey limited | Fairly limited | Fairly good | Very good | 1 | 2
Q14 | Process for making critical decisions and recommendations | Don't yet know, or very contentious and unstructured | Fairly contentious and unstructured | Fairly objective and structured | Very objective and well structured | 1 | 2
Q15 | Legal language of our airline pricing agreements | Not important or don't know | Most clauses clearly favor the airline | Some clauses favor airline, some favor us | Clear and fair language on all key clauses | 1 | 2
|  |  |  | Avg. Score | QUICK VERSION | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Goals
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
GOALS | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Clarity of Terms (on this project)
G1 | Definition of savings | Not defined, or very impractical | Fairly vague | Fairly clear | Very clear and practical | 1 | 2
G2 | Definition of quality | Not defined, or very impractical | Fairly vague | Fairly clear | Very clear and practical | 1 | 2
G3 | Definition of risk | Not defined, or very impractical | Fairly vague | Fairly clear | Very clear and practical | 1 | 2
Achievability of Goals (on this project)
G4 | For savings | Not yet set or very unrealistic | Appear very hard to meet; probably not achievable | Appear fairly hard to meet; may not be achievable | Aggressive but achievable | 1 | 2
G5 | For quality | Not yet set or very unrealistic | Appear very hard to meet; probably not achievable | Appear hard to meet; may not be achievable | Aggressive but achievable | 1 | 2
G6 | For risk | Not yet set or very unrealistic | Appear very hard to meet; probably not achievable | Appear hard to meet; may not be achievable | Aggressive but achievable | 1 | 2
Basis of Goals
G7 | Our goals are based on | Who knows - we were not consulted | Minor input from Travel department | Moderate input from Travel | Significant input from Travel department | 1 | 2
Deadlines
G8 | Given all of our other projects, our deadlines are | Definitely impossible | Only if we cut some important corners | Appear mostly achievable | Very achievable | 1 | 2
|  |  |  | Avg. Score | GOALS | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Resources
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
RESOURCES | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Airline Spend Data
R1 | Degree of consolidation | Very unconsolidated | Fairly consolidated | Mostly consolidated | Completely consolidated | 1 | 2
R2 | Market pair format | Destination cities; no origination cities | Some O&D; mostly segment or leg data | Mostly O&D; some segment or leg data | All O&D | 1 | 2
R3 | Best level of spend and segment detail | City pair or destination | City pair-airline | City pair-airline-point of sale country | City pair-airline-point of sale country-fare class | 1 | 2
R4 | Source of data | Estimates, or many unrelated agencies | General ledger, expense reports or credit cards | Mostly from a few major agencies | Single agency or data consolidator | 1 | 2
Project Team
R5 | Likely impact of our Airline Contract Analyst on success of this project | Poor or don't know | Fair | Good | Great | 1 | 2
R6 | The likely impact of our Airline Industry Expert on success of this project | Poor or don't know | Fair | Good | Great | 1 | 2
R7 | Likely impact of our Lead Negotiator on success of this project | Poor or don't know | Fair | Good | Great | 1 | 2
R8 | Likely impact of our project's Executive Sponsor on success of this project | Poor or don't know | Fair | Good | Great | 1 | 2
R9 | Budget | Clearly insufficient | Very limited | Fairly limited | Adequate or Good | 1 | 2
|  |  |  | Avg. Score | RESOURCES | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Credibility
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
CREDIBILITY | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
With our Major Airlines
CR1 | Ability to move market share | None or very limited | Fair, or fairly limited | Fairly good | Very good | 1 | 2
CR2 | Our efforts to resolve problems | None or very limited | Fair, or fairly limited | Fairly strong | Very Strong | 1 | 2
CR3 | Quality of overall relationship | Poor | Fair, or fairly limited | Good | Great | 1 | 2
With our Senior Management
CR4 | Ability to deliver the expected results | None or very limited | Fair, or fairly limited | Fairly good | Very good | 1 | 2
CR5 | Our success explaining difficult or complex issues | None or very limited | Fair, or fairly limited | Fairly good | Very good | 1 | 2
CR6 | Quality of overall relationship | Poor | Fair, or fairly limited | Good | Great | 1 | 2
|  |  |  | Avg. Score | CREDIBILITY | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Support
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
SUPPORT | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
From our Senior Management
S1 | Interest in cost savings from travel | None or very low | Fairly low | Fairly high | Very high | 1 | 2
S2 | Sensitivity to travelers' convenience | Very high | Fairly high | Fairly low | Very low | 1 | 2
S3 | Willingness to enforce travel policies | None or very low | Fairly low | Fairly high | Very high | 1 | 2
From our Travelers
S4 | Willingness to abide by key travel policies | None or very low | Fairly low | Fairly high | Very high | 1 | 2
From our Travel Agency
S5 | Willingness to sell our preferred airlines regardless of override implications | None, very low or don't know | Fairly low | Fairly high | Very high | 1 | 2
|  |  |  | Avg. Score | SUPPORT | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Control at Point of Sale
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
CONTROL AT POINT OF SALE | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Travel Policy Language
P1 | Cabin (e.g. business vs. coach) | Not mentioned | Is not very clear, or is very permissive | Clear and not very permissive | Clear and restrictive | 1 | 2
P2 | Connections | Not mentioned | Is not very clear, or is very permissive | Clear and not very permissive | Clear and restrictive | 1 | 2
P3 | Time window | Not mentioned | Is not very clear, or is very permissive | Clear and not very permissive | Clear and restrictive | 1 | 2
P4 | Price sensitivity (e.g. lowest logical fare) | Not mentioned | Is not very clear, or is very permissive | Clear and not very permissive | Clear and restrictive | 1 | 2
P5 | Booking process | Not mentioned | Is not very clear, or is very permissive | Clear and not very permissive | Clear and restrictive | 1 | 2
P6 | Exception approval process | Not mentioned | Is not very clear, or is very permissive | Clear and not very permissive | Clear and restrictive | 1 | 2
P7 | Payment process (e.g. credit card) | Not mentioned | Is not very clear, or is very permissive | Clear and not very permissive | Clear and restrictive | 1 | 2
Travel Policy Enablers
P8 | Agency consolidation | Very unconsolidated | Fairly unconsolidated | Fairly consolidated | Very consolidated | 1 | 2
P9 | Self-booking tool | None | Low adoption | Moderate adoption | High adoption | 1 | 2
P10 | Point of sale preferencing tool at agent's display | None | Depends mostly on agent's training | Preferred airlines highlighted on CRS | Preferred airlines highlighted and tied to contract goals | 1 | 2
P11 | Point of sale preferencing tool at Self-booking display | None | Preferred carriers highlighted but not often updated | Preferred airlines adjusted manually based on contract goals | Preferred airlines adjusted automatically based on contract goals | 1 | 2
P12 | Pre-trip exception reports | None or not used | Fairly ineffective | Fairly effective | Very effective | 1 | 2
P13 | Exception approval process | None or very permissive | Fairly ineffective | Fairly effective | Very effective | 1 | 2
P14 | Post-trip exception reports | None or not used | Fairly ineffective | Fairly effective | Very effective | 1 | 2
Travel Policy Compliance
P15 | Among senior management travelers | Little or none | Fairly low | Reasonably good | Very good | 1 | 2
P16 | Among middle management and other travelers | Little or none | Fairly low | Reasonably good | Very good | 1 | 2
Consequences of non-Compliance
P17 | Among senior management travelers | Few or none | Fairly light | Fairly heavy | Very heavy | 1 | 2
P18 | Among middle management and other travelers | Few or none | Fairly light | Fairly heavy | Very heavy | 1 | 2
|  |  |  | Avg. Score | CONTROL AT POINT OF SALE | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## RFP Process
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
RFP / TENDER PROCESS | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
T1 | Time given to airlines to prepare first round bids | Not yet established | Less than 10 business days to prepare bids | 11-15 business days | 15+ business days | 1 | 2
T2 | Supplier communication process | Not yet established | Process is neither very clear nor well managed | Clear but not well managed | Clear and well managed | 1 | 2
T3 | Contract negotiations | Not yet established, or very informal | Rolling throughout the year | Formal RFP process except for main airline | Formal RFP process for all suppliers at same time | 1 | 2
T4 | RFP questions for suppliers | Not yet established; or lots of detailed questions | Quite a few questions; no sytematic method for evaluating answers | Quite a few questions; good method for evaluating answers | Questions limited to key issues of price and quality; sytematic method for evaluating answers | 1 | 2
T5 | RFP data exhibits | The format has not yet been established, or will be extremely limited | Fairly limited, high-level spend data | Standard airline RFP data, well organized | Well organized and detailed data, including projected (scenario) market shares | 1 | 2
T6 | Use of online auctioning | Committed to using | Undecided | Leaning against using | Will not use | 1 | 2
T7 | Use of multi-company airline buying consortia where companies have no common ownership history | Committed to using | Undecided | Leaning against using | Will not use | 1 | 2
|  |  |  | Avg. Score | RFP / TENDER PROCESS | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Analysis
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
ANALYSIS | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Our Overall Expectations (see note below)
A1 | We expect | Either extremely detailed analyses required on most/all issues, or not much analysis expected | Either very detailed for even minor issues, or fairly limited on most issues | Solid analyses for key issues, not much for minor issues | Very solid analyses on the major issues; less so for the minor issues | 1 | 2
Level of Contract Analysis
A2 | Contract's net effective (or aggregate) discount | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
A3 | Contract's undiscounted spend | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
A4 | Value of flat or fixed fares vs. market fares | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
A5 | Comparison of fares and discounts across suppliers by market | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
Savings Analysis
A6 | Analysis of savings across a variety of scenarios | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
A7 | Allocation of savings down to the business unit or country level (1 level below parent) | Important, but we won't be able to do any analysis | Important; but we'll do only a fairly limited analysis | Either not very important in our firm; or we'll do a fairly good analysis | Either not very important in our firm; or we'll do a very good analysis | 1 | 2
Quality Analysis
A8 | Airline-specific quality scoring | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
A9 | Quality implications for each scenario | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
Contract Risk Analysis
A10 | Evaluating each goal for risk of non-achievability | An "eyeball" estimate | Fairly limited | Fairly comprehensive | Very comprehensive | 1 | 2
|  |  |  | Avg. Score | ANALYSIS | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
*There is definitely an art to balancing the benefit of detailed analysis against the limited resources of the team. Corporate cultures clearly play a big role in setting these analytical expectations. Travel Analytics believes most project teams will benefit by having a much more solid set of facts and analyses at hand for the major issues, and therefore the extra work on these key issues will, in the long run, reduce project stress and increase the project's success. The criteria for low stress/high stress on this page reflect this view.
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Negotiations
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
NEGOTIATIONS | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Key Factors Affecting Negotiations
N1 | Understanding of yield management | What's yield management? | Basic awareness | Fairly good understanding | Very good understanding | 1 | 2
N2 | Understanding the rationale behind airline discounts | It's all based on volume - isn't it? | Basic awareness | Fairly good understanding | Very good understanding | 1 | 2
N3 | Importance of a strong travel policy | Why does our travel policy matter? | Know it's important, but we can't strengthen it | Important, but limited ability to strengthen it | Important and clearly able to strengthen it | 1 | 2
N4 | Understanding of how low-cost carriers affect our negotiations | Seems to be a very big issue for us; not sure how to analyze this | Appears to be a fairly important issue for us | Fairly clear understanding; or not much of an issue | Very clear understanding; or not at all an issue | 1 | 2
N5 | Codeshare and alliance pricing | Fairly big issue but unsure how to best negotiate on this issue | Fairly big issue; we have a basic understanding of the negotiating implications | Negotiating implications for our account are fairly clear; or not a big issue | Negotiating implications for our account are very clear; or not at all an issue | 1 | 2
N6 | Understanding of what each key airline wants most from our account | We don't really know, other than as much revenue as possible | Fairly limited understanding | Fairly good understanding | Very clear understanding | 1 | 2
N7 | Credibility of our promises of incremental revenue and threats of lost business | Very low or no credibility | Fairly low credibility | Good credibility | Strong credibility | 1 | 2
N8 | Quality of our feedback to each airline on how to improve its pricing | We tell the airline to improve its offer - that's about it | Some general guidelines and requests | Fairly specific guidelines and requests | Very specific requests | 1 | 2
N9 | Quality of our feedback to each airline on how to improve their goals | We don't worry about negotiating the goals | We tell the airline to reduce their goals - that's all | Fairly specific guidelines and requests | Very specific requests | 1 | 2
N10 | Overall confidence in our ability to move market share as required to meet key airline goals | Very low or no confidence | Fairly low confidence | Fairly high confidence | Very high confidence | 1 | 2
|  |  |  | Avg. Score | NEGOTIATIONS | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Decisions
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
DECISIONS | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Key Criteria
D1 | Savings Criteria | Not defined | Vaguely defined | Fairly well defined | Very well defined | 1 | 2
D2 | Quality Criteria | Not defined | Vaguely defined | Fairly well defined | Very well defined | 1 | 2
D3 | Risk Criteria | Not defined | Vaguely defined | Fairly well defined | Very well defined | 1 | 2
Constraints (Least Acceptable Positions)
D4 | Minimum Savings | Not defined | Vaguely defined | Fairly well defined | Very well defined | 1 | 2
D5 | Minimum Quality | Not defined | Vaguely defined | Fairly well defined | Very well defined | 1 | 2
D6 | Maximum Risk | Not defined | Vaguely defined | Fairly well defined | Very well defined | 1 | 2
Reciprocity
D7 | Potential for supplier(s) to influence decisions due to purchases of our goods or services | Definitely an issue, but we have no clear method of resolving this | Will likely be an issue that affects our decision, but we have a fairly clear method of resolving this | Probably will not be an issue | Clearly not an issue | 1 | 2
Parent vs. Business Units
D8 | Likely decider of supplier selections | This is a very messy issue with no clear answer or process for resolving it | Business units will clearly have the right to opt out if they are not going to benefit | Business units will be consulted, but they'll have little ability to opt out | Selections are clearly driven by what's best for the parent | 1 | 2
Recommendation Process
D9 | Potential impact of personal biases | Potentially very high | Potentially fairly high | Fairly low | Very low | 1 | 2
D10 | Ability to resolve dissenting views before making recommendation to senior management | Likely to be a source of major friction among our team | Not very confident in our abilities | Fairly confident in our abilities | Very confident in our abilities | 1 | 2
Stakeholders
D11 | Number of individuals involved in evaluating detail of RFP responses | Not yet defined, or more than 10 people | 7 to 10 people | 4 to 6 people | 3 or fewer people | 1 | 2
D12 | Number of individuals needed to decide which airlines win our business | Not yet defined, or more than 10 people | 7 to 10 people | 4 to 6 people | 3 or fewer people | 1 | 2
D13 | Roles and responsibilities | Not yet defined | Not well defined; likely to cause conflicts | Fairly well defined | Very well defined and practical | 1 | 2
D14 | Manageability of the decision process | Don't yet know, or very unmanageable | Difficult to manage | Not very difficult to manage | Fairly easy to manage | 1 | 2
|  |  |  | Avg. Score | DECISIONS | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Contracting
|  | (High Stress / Low Success) |  |  | (Low Stress / High Success) | Score
CONTRACTING | [5 empty] | Now | Most Likely
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4
Contracting Process
CO1 | Legal input and issues raised within our team | Not sought, or sought late in project | Sought fairly late; or input not very helpful | Sought fairly early, and input fairly helpful | Sought very early, and input very helpful | 1 | 2
CO2 | Contract issues raised with airlines | Very late in the process | Fairly late in the process | Fairly early in the process | Very early in the process | 1 | 2
Contract Elements
CO3 | Definition of goals | Not well defined, or defined clearly to the airline's advantage | Will need to be defined clearly to our advantage | Definitions are OK; we're comfortable with the uncertainties | Clearly defined in a fair and reasonable manner | 1 | 2
CO4 | Method for adjusting / indexing goals | Not an important issue, or no method in contract | Method relies soley on airline's calculations | Method allows for equitable adjustment | Method relies primarily on neutral third party's calculations | 1 | 2
CO5 | Method of measuring performance against goals | Not an important issue, or no method in contract | We have to take the airline's word as final | Method relies primarily on airline's calculations, but contract lets us appeal | Method relies primarily on neutral third party's calculations | 1 | 2
CO6 | Codeshare partner pricing terms | Contract is silent | Not very clear, or is very restrictive | Fairly clear and permissive | Very clear and permissive | 1 | 2
CO7 | Consequences of not meeting a goal | Airline has right to quickly cancel our entire contract and seek damages against us | Airline has right to quickly cancel our entire contract, but can't seek damages | Airline has right to quickly reduce discounts only on markets covered by the failed goal | We have a reasonable amount of time to cure any shortfall; discounts can be cancelled only on markets covered by a failed goal | 1 | 2
CO8 | Protection against factors not within our control | Contract is silent | Contract contains force majeure clause | Satisfaction of segment share goal(s) will override revenue or revenue share shortfall | We are protected against all major factors outside of our control | 1 | 2
|  |  |  | Avg. Score | CONTRACTING | 1 | 2
1.0
0.5
2.0
3.0
4.0
1.5
2.5
3.5
4.5
Read the four criteria that relate to the elements in Column C, and select the score (between 0.5 and 4.5) that best reflects your "Now" (current) and "Most Likely" positions. "Most Likely" should reflect the score you expect to achieve at whatever time in the project the issue is relevant. For example, most Decision and Contract issues won't be relevant until later in the project. You may give these issues a low "Now" score but a higher "Most Likely" score if you're confident those issues will not be a problem at that stage of the project,

## Scores
Airline Sourcing Project Stress Test
Provided by Travel Analytics | [5 empty] | Dimension Scores (Detailed Questions)
|  | Now |  | Most Likely
Quick Score |  | 1 |  | 2
Overall Detailed Score* |  | 1 |  | 2
Scores by Dimension | Weight*
GOALS | 10% | 1 | 0.1 | 2 | 0.2
RESOURCES | 10% | 1 | 0.1 | 2 | 0.2
CREDIBILITY | 10% | 1 | 0.1 | 2 | 0.2
SUPPORT | 10% | 1 | 0.1 | 2 | 0.2
CONTROL AT POINT OF SALE | 10% | 1 | 0.1 | 2 | 0.2
RFP / TENDER PROCESS | 10% | 1 | 0.1 | 2 | 0.2
ANALYSIS | 10% | 1 | 0.1 | 2 | 0.2
NEGOTIATIONS | 10% | 1 | 0.1 | 2 | 0.2
DECISIONS | 10% | 1 | 0.1 | 2 | 0.2
CONTRACTING | 10% | 1 | 0.1 | 2 | 0.2
Total weights | 100%
* By default, the overall score is an equally weighted average of the scores within each of the
ten categories. If you want the individual dimensions to be weighted differently, please adjust
the percentages in the yellow-shaded cells above.